## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Environment setup and API configuration ( NewsAPI key) | MUST HAVE | NewsAPI | V Naga Harshitha | 3- Completed
S1 | S1 | US-002 | Data collection and cleaning of AI/ML news articles | MUST HAVE | NewsAPI | V Naga Harshitha | 3- Completed
S2 | S2 | US-003 | Multi-source data aggregation (NewsAPI + GNews) | MUST HAVE | BeautifulSoup,RSS Feeds | V Naga Harshitha | 3- Completed
S2 | S2 | US-004 | Sentiment analysis using Gemini API | MUST HAVE | Gemini API,Hugging Face Transformers | V Naga Harshitha | 3- Completed
S3 | S3 | US-005 | Forecast model implementation using Prophet (predict sentiment trends) | SHOULD HAVE | Prophet,Pandas | V Naga Harshitha | 3- Completed
S3 | S3 | US-006 | Slack alert system integration for abnormal sentiment shifts | SHOULD HAVE | Slack SDK | V Naga Harshitha | 3- Completed
S4 | S4 | US-007 | Streamlit dashboard design and visualization setup | MUST HAVE | Streamlit,Matplotlib | V Naga Harshitha | 3- Completed
S4 | S4 | US-008 | Final testing, validation, and deployment of dashboard | MUST HAVE | All Modules Integrated,Streamlit Cloud,GitHub | V Naga Harshitha | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 38 | 9 | 8 | 7 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T1 | Environment setup (Python, googlecolab, Git setup) | 2025-08-18 | 2025-08-21 | V.Naga Harshitha | Setup | Completed | 3 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T2 | Connect and test APIs (NewsAPI,Gnews) | 2025-08-21 | 2025-08-22 | V.Naga Harshitha | Data Collection | Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T3 | Build Sentiment Analysis Engine using Gemini API | 2025-08-28 | 2025-08-29 | V.Naga Harshitha | Development | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T4 | Aggregate and clean data using pandas | 2025-09-03 | 2025-09-04 | V.Naga Harshitha | Data Cleaning | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T5 | Forecasting model using prophet | 2025-09-10 | 2025-09-13 | V.Naga Harshitha | Model Training | Completed | 6 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T6 | Integrate Slack API for alerts | 2025-09-15 | 2025-09-18 | V.Naga Harshitha | Integration | Completed | 9 | 1 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T7 | Build visualization dashboard (matplotlib/seaborn) | 2025-09-22 | 2025-10-26 | V.Naga Harshitha | Dashboard | Completed | 5 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T8 | Deploy Streamlit dashboard | 2025-10-01 | 2025-10-06 | V.Naga Harshitha | Deployment | Completed | 3 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | API key missing in google keys | Added NEWS_API_KEY, GNEWS-API in google colab Keys
Sprint 1 | Day4 | Errors while fetching NewsAPI articles. | Debugged query and successfully fetched 1000 AI/ML articles.
Sprint 2 | Day14 | Not giving sentimental score | give the required prompt
Sprint 2 | Day16 | Duplicate articles across sources | Implemented filtering for AI-related keywords only
Sprint 3 | Day 24 | Getting slack api | search different source to create generate slackapi and create channel
Sprint 4 | Day 36 | Pivot tables and visualizations misaligned | Created pivot tables for sentiment, mentions, share of voice and dashboard
Sprint 4 | Day 40 | Alert and anomaly detection complex | Implemented IsolationForest anomaly detection and alert table

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-08-21 | 2025-08-25 | V Naga Harshitha | Set up Python environment and configure API keys; Start fetching AI/ML news. | Manually cleaning unstructured data. | Using .env for secure API key storage. | Successfully collected initial dataset and saved cleaned CSV for downstream tasks.
2 | Sprint 2 | 2025-09-03 | 2025-09-10 | V Naga Harshitha | Aggregate news from multiple sources; Integrate Gemini API for sentiment. | Using single-source news only. | Using LLMs for sentiment classification. | Combined geminiAPi& NewsAPI articles, filtered AI-related content, saved multi_source_ai_sentiment.csv.
3 | Sprint 3 | 2025-09-15 | 2025-09-23 | V Naga Harshitha | Implement trend forecasting with Prophet; Configure Slack alerts. | Manually monitoring trends. | Automating sentiment detection and alerts. | Forecasted sentiment trends, sent automated Slack alerts, orchestrated pipeline with main.py.
4 | Sprint 4 | 2025-09-25 | 2025-10-05 | V Naga Harshitha | Build Streamlit dashboard with interactive filters and visualizations. | Static visualizations only. | Using matplotlib/seaborn and anomaly detection. | Deployed interactive Strategic Intelligence Dashboard (app.py) with forecasts, alerts, and CSV export.